## Sheet1
Task_Id | Module Name | Task Name | Priority | Assign To | Efforts in Man Hours | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status
T-01 |  | Functional Specification Document Version 1 |  | Mohit | 8 | 2025-08-24 | 2025-08-25 | 2025-08-24 | 2025-08-26 | close
T-02 |  | Functional Specification Document Version 2 |  | Mohit | 2 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-29 | close
T-03 |  | Functional Specification Document Version 3 |  | Mohit | 2 | 2025-08-26 | 2025-08-28 | 2025-08-29 | 2025-09-03 | close
T-04 |  | Functional Specification Document Version 4 |  | Mohit | 1 | 2025-08-30 | 2025-09-08 | 2025-09-09 | 2025-09-16 | close
T-05 |  | Technical Specification Document Version 1 |  | Vaishnavi |  | 2025-09-03 | 2025-09-09 | 2025-09-04 | 2025-09-09 | close
T-06 |  | Techincal Specification Document Version 2 |  | Vaishnavi |  | 2025-09-12 | 2025-09-26 | 2025-09-12 | 2025-09-26 | close
T-07 |  | High Level Design Version 1 |  | Siddesh | 4 | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-26 | close
T-08 |  | High Level Design Version 2 |  | Siddesh | 3 | 2025-08-28 | 2025-09-29 | 2025-09-28 | 2025-09-29 | close
T-09 |  | High Level Design Version 3 |  | Siddesh | 7 | 2025-09-01 | 2025-09-02 | 2025-09-01 | 2025-09-02 | close
T-10 | TTMS | Test Case Document Version 1 |  | Ajinkya |  | 2025-10-01 | 2025-10-02 | 2025-10-01 | 2025-10-02 | close
T-11 | Employee | Frontend:Employee Dashboard-Design Stats card |  | Ajinkya | [5 empty] | close
T-12 | Employee | Frontend:Employee Dashboard-Stats Card Data Fetching |  | Ajinkya | [5 empty] | close
T-13 | Employee | Backend:Employee Dashboard-API for count employeees with postmon testing |  | Siddesh | 0.5 |  |  |  |  | close
T-14 | Employee | Frontend:Employee Dashboard-Table UI Design |  | Ajinkya | [5 empty] | close
T-15 | Employee | Backend:Employee Dashboard-API to fetch the data with postmon testing |  | Siddesh | 0.5 |  |  |  |  | close
T-16 | Employee | Frontend:Employee Management |  | Ajinkya | [5 empty] | close
T-17 | Employee | Backend:API to manage the employee |  | Siddesh | 4 |  |  |  |  | close
T-18 | Employee | Frontend:Request Creation UI Design |  | Ajinkya | [5 empty] | close
T-19 | Employee | Backend:Request Creation API |  | Siddesh | 6 |  |  |  |  | close
T-20 | Employee | Frontend:Profile Design |  | Ajinkya | [5 empty] | close
T-21 | Employee | Backend:API to fetch the user details |  | Siddesh | 0.5 |  |  |  |  | close
T-22 | All | Backend:Login API with support of cookie storage on client machine |  | Siddesh | 1.5 |  |  |  |  | close
T-23 | All | Backend:Logout API with support of cookie destruction from client machine |  | Siddhesh | 1.5
T-24 | HR | Frontend:HR Dashboard-UI Design of stats card |  | Vaishnavi | [5 empty] | close
T-25 | HR | Frontend:HR Dashboard-Stats card data fetching |  | Vaishnavi | [5 empty] | close
T-26 | HR | Backend:API to fetch the data to count employees |  | Siddesh | 0.5 |  |  |  |  | close
T-27 | HR | Frontend:HR Dashboard-Table UI Design |  | Vaishnavi | [5 empty] | close
T-28 | HR | Frontend:HR Dashboard-Fetch the recent employees |  | Vaishnavi | [5 empty] | close
T-29 | HR | Backend:API to fetch the employees |  | Siddesh | 0.5 |  |  |  |  | close
T-30 | HR | Backend:API To fetch pending approval data |  | Siddesh | 4 |  |  |  |  | close
T-31 | HR | Frontend:Employee Management UI |  | Vaishnavi | [5 empty] | close
T-32 | HR | Backend:API for employee management |  | Siddesh | 5 |  |  |  |  | close
T-33 | HR | Frontend:Approval Workflow UI |  | Vaishnavi | [5 empty] | close
T-34 | HR | Frontend:Request Fetching |  | Vaishnavi | [5 empty] | close
T-35 | HR | Backend:Approval Workflow API |  | Siddesh | 7 |  |  |  |  | close
T-36 | HR | Frontend:Exception Page UI |  | Vaishnavi | [5 empty] | close
T-37 | HR | Frontend:Reimbursement Page UI |  | Vaishnavi | [5 empty] | close
T-38 | HR | Frontend:HR Profile UI+Fetching data |  | Vaishnavi | [5 empty] | close
T-39 | HR | Backend:API to fetch the HR details |  | Siddesh | 0.5 |  |  |  |  | close
T-40 | Manager | Frontend:Manager Dashboard-Stats card design |  | Vaishnavi | [5 empty] | close
T-41 | Manager | Frontend:Manager Dashboard-count fetching for stats card |  | Vaishnavi | [5 empty] | close
T-42 | Manager | Backend:API to fetch the real time data |  | Siddesh | 0.5 |  |  |  |  | close
T-43 | Manager | Frontend:Table design-Recent Request(UI+Fetching) |  | Vaishnavi | [5 empty] | close
T-44 | Manager | Frontend:Table desgin-Pending Approval(UI+Fetching) |  | Vaishnavi | [5 empty] | close
T-45 | Manager | Backend:API to fetch real time request data |  | Siddesh | 0.5 |  |  |  |  | close
T-46 | Manager | Frontend:Team Request page(UI+Fetching) |  | Vaishnavi | [5 empty] | close
T-47 | Manager | Backend:API for team request |  | Siddesh | 5 |  |  |  |  | close
T-48 | Manager | Frontend:Manager Profile(UI) |  | Vaishnavi | [5 empty] | close
T-49 | Travel Desk | Frontend:Validation Queue(Fetching) |  | Ajinkya | [5 empty] | close
T-50 | Travel Desk | Frontend:Approval Workflow |  | Ajinkya | [5 empty] | close
T-51 | Finance | Frontend:Pending Approval(Fetching) |  | Ajinkya | [5 empty] | close
T-52 | Super Admin | Frotend:Dashboard UI Design |  | Vaishnavi | [5 empty] | close
T-53 | Super Admin | Frontend:Dashboard Page CSS |  | Vaishnavi | [5 empty] | close
T-54 | Super Admin | Frontend:User Management UI+CSS |  | Vaishnavi | [5 empty] | close
T-55 | Super Admin | Frontend:Policy Management UI+CSS |  | Vaishnavi | [5 empty] | close
T-56 | Super Admin | Frontend:SLA page UI Design |  | Vaishnavi | [5 empty] | close
T-57 | Super Admin | Frontend:Reports Page UI Design |  | Vaishnavi | [5 empty] | close
T-58 | Super Admin | Frontend:System logs page+ Override Approval page UI design |  | Vaishnavi | [5 empty] | close
T-59 |  | Backend:Employee Management servcie Task - Emp Creation,Editing data, project assignement,manager assignement, employee roles |  | Siddesh | 7 |  |  |  |  | close
T-60 |  | Backend:Policy Management Service(Working) policy creation, data handaling , policy versioning, City creation ,City Category creation and alignment with policy |  | Siddesh | 10 |  |  |  |  | close
T-61 |  | Backend:Travel Request Service: Task - Request Creation, Booking Controllers, Wokflow Initialization using workflow service, bill attachment support |  | Siddesh | 14 |  |  |  |  | close
T-62 |  | Backend:Inter Service communication POC+Testing , established connection within employee management service with travel request management service and workflow creation service |  | Siddesh | 3 |  |  |  |  | close
T-63 |  | Backend:Security Implementation(All Services) Security configuration with all services |  | Siddesh | 5 |  |  |  |  | close
T-64 |  | Backend:Authentication service creation for login and registration of employee and integereated with spring security, API getway and with other service, configuration work for all services , Advanced Data encryption of user and cookies stroring on client browser while logging with cookie destroying support from client browser while logout. |  | Siddesh | 15 |  |  |  |  | close
T-65 |  | Backend:Integration with employee management service, service connection established for role featching for role based login support |  | Siddesh | 4 |  |  |  |  | close
T-66 |  | Backend:Authentication service integration with all services with respect to security |  | Siddesh | 6 |  |  |  |  | close
T-67 |  | Backend:POC With API Gateway + Integration Testing with all services |  | Siddesh | 3 |  |  |  |  | close
T-68 |  | Backend:API gateway Implementation , route handaling , security filters , validation of interservice communcation and enforcement of api calls through api getway, moved on netty server to serve better API call rounting between service using spring webflux stack |  | Siddesh | 6 |  |  |  |  | close
T-69 |  | Backend:API Gateway Final Integration and routing with all service, Security Inforcment on api calls confirm , rounting Confirm with specified paths. |  | Siddesh | 3 |  |  |  |  | close
T-70 |  | Backend:Performace testing between travel request management + Approval workflow service (Key findings interservice's calls are blocking thread because of synchronous nature of tomcat server while handaling of api calls ) |  | Siddesh | 8 |  |  |  |  | close
T-71 |  | Backend:optimization between travel request management + Approval workflow service(In-working optimization needed) so far reduction in interserice call for data , improved performance acheived from reduced calls between services, working on furtuer research for looscoupling of services, and started find new solution like kafka zookeper , RabbitMQ to remove dependent neature of API calls for data |  | Siddesh | 7 |  |  |  |  | Open
T-72 |  | Backend:optimization research for travel request management + Approval workflow service using event streaming(kafka) |  | Siddesh | 30 |  |  |  |  | Open
T-73 |  | Backend:Architectural research for notification service using event streaming (kafka) and testing with other services |  | Siddesh | 12 |  |  |  |  | Open
T-74 |  | Backend:Architectural research for finance service (tooling + integration with travel request management ) |  | Siddesh | 14 |  |  |  |  | Open
T-75 |  | Backend:Research require for file storage of bills and reports with travel request management |  | Siddesh | 3 |  |  |  |  | Open
T-76 |  | Backend:API Gateway optimzation is doable(In-process) |  | Siddesh | 4 |  |  |  |  | Open
T-77 | Manager | Frontend:Count fetching and API Handling for Stat Card | P1 | Vaishnavi | 1 |  |  |  |  | Open
T-78 | Manager | Frontend:Logs Data(Fetching+UI) | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-79 | Manager | Frontend:Logout(Functionality) | P2 | Vaishnavi | 0.5 |  |  |  |  | Open
T-80 | Manager | Backend:Policy integration+Code optimization |  | Siddesh | 6 |  |  |  |  | Open
T-81 | Manager | Frontend:Manager Pofile Data Fetching | P1 | Vaishnavi | 0.5 |  |  |  |  | Open
T-82 | Manager | Frontend:Request Creation CSS handling+Polishment | P1 | Vaishnavi | 2 |  |  |  |  | Open
T-83 | Manager | Frontend:Recent Request fetching and Management+ CSS Polishment | P1 | Vaishnavi | 1 |  |  |  |  | Open
T-84 | Manager | Frontend: Request Detail Page UI | P2 | Vaishnavi | 0.5
T-85 | Manager | Frontend:Request Management and filtering and updation | P1 | Vaishnavi | 1.5 |  |  |  |  | Open
T-86 | HR | Backend:Policy Management+Code Optimization |  | Siddesh | 4 |  |  |  |  | Open
T-87 | Manager | Frontend:Apply Filter and Search bar to all tables | P3 | Vaishnavi | 0.5 |  |  |  |  | Open
T-88 | Manager | Frontend:Handle the pagination in the team request page i.e the request which are pending for approval from manager | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-89 | HR | Frontend:Logout(Functionality) | P2 | Vaishnavi | 0.5 |  |  |  |  | Open
T-90 | HR | Frontend:Exception Request Fetching | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-91 | HR | Frontend:Reimbursement Page data fecthing | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-92 | HR | Frontend:Approval workflow (Reject Request with the some information) | P1 | Vaishnavi | 0.5 |  |  |  |  | Open
T-93 | HR | Frontend:History logs Page Fetching data + Pagination | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-94 | HR | Frontend:Employee Management UI issue resolve(Animation and effects and polishing) | P3 | Vaishnavi | 0.5 |  |  |  |  | Open
T-95 | HR | Frontend:Exception Page data handling and apply filter and validation | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-96 | HR | Frontend:Employee Profile Management UI | P2 | Vaishnavi | 0.5
T-97 | HR | Frontend:Approval Request detailed workflow UI with remarks and audit trail | P3 | Vaishnavi | 0.5
T-98 | HR | Frontend:Data filtering | P3 | Vaishnavi | 0.5 |  |  |  |  | Open
T-99 | Employee | Frontend:UI+Routing for Quick Actions - Stat Card | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-100 | Employee | Frontend:Request Creation CSS handling+Polishment | P1 | Ajinkya | 1 |  |  |  |  | Open
T-101 | Employee | Frontend:My Request CSS Polishment | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-102 | Employee | Frontend:User Profile UI handling+CSS Polishment | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-103 | Employee | Frontend:Logout Functionality | P2 | Ajinkya | 0.5 |  |  |  |  | Open
T-104 | Travek Desk | Frontend:Dashboard(Fetch)+CSS Polishment | P1 | Ajinkya | 1 |  |  |  |  | Open
T-105 | Travek Desk | Frontend:Validation Queue CSS Polishment | P1 | Ajinkya | 1 |  |  |  |  | Open
T-106 | Travek Desk | Frontend:Booking queue CSS polishment+handeling | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-107 | Travek Desk | Frontend:Booking History CSS + Fetching of the requests | P3 | Ajinkya | 1 |  |  |  |  | Open
T-108 | Travek Desk | Frontend:Reports Fetching+CSS | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-109 | Travek Desk | Frontend:Exception Page UI + CSS improvement | P1 | Ajinkya | 1 |  |  |  |  | Open
T-110 | Travek Desk | Frontend:Logout(Functionality)+CSS handling | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-111 | Finance | Frontend:Dashboard-stats card fetching+UI+CSS | P2 | Ajinkya | 1 |  |  |  |  | Open
T-112 | Finance | Frontend:Dashboard-Budget utilization UI+Real time fetching | P3 | Ajinkya | 0.5 |  |  |  |  | Open
T-113 | Finance | Frontend:Pending Appoval CSS handling | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-114 | Finance | Frontend:Reimbursement Page UI+Fetching data | P2 | Ajinkya | 1 |  |  |  |  | Open
T-115 | Finance | Frontend:Reimbursement Page CSS handling | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-116 | Finance | Frontend:Budget tracking Page UI+Fetching data+CSS | P3 | Ajinkya | 1 |  |  |  |  | Open
T-117 | Finance | Frontend:Policy Exception Page UI+Fetching data+CSS | P2 | Ajinkya | 1 |  |  |  |  | Open
T-118 | Finance | Frontend:History logs Page UI+Fetching data+CSS | P3 | Ajinkya | 1 |  |  |  |  | Open
T-119 | Finance | Frontend:Reports page UI+Fetching+CSS | P2 | Ajinkya | 1 |  |  |  |  | Open
T-120 | Finance | Frontend:Logout(Functionality)+CSS Handling | P1 | Ajinkya | 0.5 |  |  |  |  | Open
T-121 | Super Admin | Frontend:Stats card data fecthing with API | P1 | Vaishnavi | 0.5 |  |  |  |  | Open
T-122 | Super Admin | Frontend:Real data and reports loading | P1 | Vaishnavi | 3 |  |  |  |  | Open
T-123 | Super Admin | Frontend:Real time policy loading and management (Update,Delete) | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-124 | Super Admin | Frontend:Add Policy Functionality | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-125 | Super Admin | Frontend:SLA Setting to work with real time data and API | P2 | Vaishnavi | 1 |  |  |  |  | Open
T-126 | Super Admin | Frontend:Reports functionality with API and real time data | P3 | Vaishnavi | 2 |  |  |  |  | Open
T-127 | Super Admin | Frontend:System logs functionality to display the prevoius request with the Backend API | P3 | Vaishnavi | 0.5 |  |  |  |  | Open
T-128 | Super Admin | Frontend:Logout(Functionality)+CSS Handling | P1 | Vaishnavi | 0.5 |  |  |  |  | Open
T-129 | Super Admin | Backend:Code Optimization (Analysis and optimization) |  | Siddesh | 30 |  |  |  |  | Open
T-130 | Super Admin | Backend:Reports & Management |  | Siddesh | 14 |  |  |  |  | Open
T-131 | Super Admin | Frontend:Override apporval(Fetching)+ API Handling | P3 | Vaishnavi | 1 |  |  |  |  | Open
T-132 | All | folder restrcturing and code optimzation and review For all modules | P3 | Vaishnavi | 3 |  |  |  |  | Open
T-133 | Travel Desk | Folder restructuring and code optimization and review | P4 | Ajinkya | 1 |  |  |  |  | Open
T-134 | Employee | Folder restructuring and code optimization and review | P4 | Ajinkya | 1 |  |  |  |  | Open
T-135 | Finance | Folder restructuring and code optimization and review | P4 | Ajinkya | 1 |  |  |  |  | Open
T-136 | All | Form validation consistency across all request forms | P1 | Vaishnavi | 2
T-137 | All | Frontend:Message handling though resource file | P4 | Vaishnavi | 16 |  |  |  |  | Open
T-138 | All | Code testing, performance testing and Bug Fixing | P4 | Vaishnavi,Ajinkya,Siddhesh | 24
T-139 | All | Deploy on QA & Testing in QA | P1 | Vaishnavi,Ajinkya,Siddhesh,Mohit | 24 |  |  |  |  | Open
T-140 | All | Bug Fixing and Deploy & Test on QA | P1 | Vaishnavi,Ajinkya,Siddhesh,Mohit | 24
T-141 | All | UAT | P1 | Mohit | 24 |  |  |  |  | Open
T-142 | All | Bug Fixing and Deploy & Test on QA | P1 | Mohit | 16
T-143 | All | Deploy on Production | P1 | Mohit | 16